## Tabelle1
Risk assesment
Lp. | The Main of Risk | Reason/cause | Probability in % | Impact from 1-10 | Level of Risk | Risk response Strategy | Person in Charge
Designing Risk
1 | Time is running short | Scope is to large for the given time | 75% | 8 | 6 | Working on it early, clearing To-Dos | Elia
2 | Youtrack failiure | Lost of youtrack and backup can't get reinstalled | 70% | 8 | 5.6 | Schedule Backups for the instance, contact support for help | Tim
3 | Wrong focus | Focusing to much on details than the whole picture | 55% | 5 | 2.75 | Time tracking of the issues | Elia
4 | Delay of Parts for the Machine | Delays in Delivery or a spontanious pandemic in the whole world | 20% | 8 | 1.6 | Reorder it! | Anna
5 | Server failiure | Servercontract can't get extended till after june / Serverbackup isn't working on new server | 20% | 7 | 1.4 | Verify asap | Tim
6 | Hardware failiure | Pi isn't working with the rest of the machine / Pumps are not proper managable | 15% | 10 | 1.5 | Tests with the Hard- and Software | Elia
7 | Server hardware to weak | We unterestimeted the performance needed for the database | 10% | 2 | 0.2 | Get replacement or upgrade as fast as possible | Tim
8 | Private Issues | Peronal circumstances / A member gets sick or is not fully available for the project | 10% | 6 | 0.6 | Nothing we can really do | Everyone
9 | University Dropout | Someone of the team gets deregistered | 2% | 8 | 0.16 | Lerning, in case of dropout decrease scope | Everyone
10 | Data loss | Data gets lost due to bugs or Servererrors | 1% | 10 | 0.1 | Git and Server backups | Everyone